## Sheet1
NO | ACTIVITIES | PAGE | STATUS | LACK | DEPENDENCY ACTIVITY | STATUS LAST UPDATE | TODAY
1 | user account register | CreateAccount | ALMOST | !yet configured: ppicture file upload | - | 2022-01-06 22:44 | 2022-01-07 21:41
2 | user view profile | UserLogin | ALMOST | !yet configured: ppicture file download | 1 | 2022-01-07 15:15
3 | user update profile | - | ALMOST | !yet configured: ppicture file download | 2 | 2022-01-07 21:41
4 | user delete account | UserProfile | DONE | - | 2 | 2022-01-07 18:22
5 | user add contact | CreateContact | ALMOST | !yet configured: ppicture file upload | 2 | 2022-01-06 22:44
6 | user view contact | ContactDetails | ALMOST | !yet configured: ppicture file download | 2 | 2022-01-06 22:44
7 | user delete contact | ContactDetails | ALMOST | require real contact_id | 6 | 2022-01-07 11:08
8 | user update contact | ContactDetails | ALMOST | require real contact_id,fk_contact_type_id | 6 | 2022-01-07 13:30
9